## Project Overview
PROJECT PLANNER & TIMELINE
PROJECT DETAILS
Project Name: | Enter Project Name
Project Manager: | Enter Name
Start Date: | 01/01/2026
Target End Date: | 31/03/2026
Status: | In Progress
Priority: | High
PROJECT SUMMARY
Metric | Value | Target | Status
Total Tasks |  | 20
Completed |  | 20
In Progress |  | 0 | -
Not Started |  | 0 | -
Completion % |  | 100%

## Tasks
TASK LIST
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Notes
T001 | Project Kickoff Meeting | Project Manager | 01/01/2026 | 01/01/2026 | Complete | High | Initial planning
T002 | Requirements Gathering | Business Analyst | 02/01/2026 | 10/01/2026 | Complete | High | Stakeholder interviews
T003 | Design Phase | Designer | 11/01/2026 | 25/01/2026 | In Progress | High | UI/UX design
T004 | Development Sprint 1 | Developer | 26/01/2026 | 09/02/2026 | Not Started | High | Core features
T005 | Development Sprint 2 | Developer | 10/02/2026 | 24/02/2026 | Not Started | Medium | Additional features
T006 | Testing Phase | QA Team | 25/02/2026 | 10/03/2026 | Not Started | High | Full testing
T007 | Documentation | Technical Writer | 01/03/2026 | 15/03/2026 | Not Started | Medium | User guides
T008 | Deployment | DevOps | 16/03/2026 | 20/03/2026 | Not Started | High | Production release
T009 | Training | Project Manager | 21/03/2026 | 25/03/2026 | Not Started | Medium | User training
T010 | Project Closure | Project Manager | 26/03/2026 | 31/03/2026 | Not Started | Low | Final review

## Gantt Chart
PROJECT GANTT CHART
Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Project Kickoff
Requirements
Design Phase
Development Sprint 1
Development Sprint 2
Testing Phase
Documentation
Deployment
Training
Project Closure

## Milestones
PROJECT MILESTONES
Milestone | Target Date | Actual Date | Status | Notes
Project Approved | 01/01/2026 | 01/01/2026 | Complete | Stakeholder sign-off
Requirements Complete | 10/01/2026 | 10/01/2026 | Complete | Documented and approved
Design Approved | 25/01/2026 |  | Pending | Awaiting review
Development Complete | 24/02/2026 |  | Pending
Testing Complete | 10/03/2026 |  | Pending
Go-Live | 20/03/2026 |  | Pending | Production deployment
Project Closure | 31/03/2026 |  | Pending | Final sign-off

## Resources
TEAM RESOURCES
Name | Role | Email | Allocation % | Tasks Assigned
John Smith | Project Manager | john@example.com | 100% | 3
Jane Doe | Business Analyst | jane@example.com | 50% | 1
Bob Wilson | Designer | bob@example.com | 100% | 1
Alice Brown | Developer | alice@example.com | 100% | 2
Charlie Davis | QA Tester | charlie@example.com | 75% | 1
Eve Johnson | Technical Writer | eve@example.com | 50% | 1

## Instructions
HOW TO USE THIS PROJECT PLANNER
1. PROJECT OVERVIEW
- Fill in project details at the top
- Summary updates automatically based on tasks
2. TASKS
- Add all project tasks with dates and assignments
- Update status: Complete, In Progress, Not Started
- Set priority: High, Medium, Low
3. GANTT CHART
- Visual timeline of all tasks
- Update bars manually when schedule changes
4. MILESTONES
- Track key project milestones
- Record actual completion dates
5. RESOURCES
- List team members and their roles
- Track allocation percentages
Created by Ayoolumi Melehon ¦ ayofemimelehon.com